## Cover
Domestic Private Sector Workload Estimate
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
CMAV Workload FY26 Q4 – FY27 Q3 as of 30 JULY 2026
Industry Version
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
PAE MARITIME

## MARMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2025-12-15 | 2026-08-28 | 257
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2026-05-11 | 2026-07-31 | 82
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2026-05-18 | 2026-07-02 | 46
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2026-07-17 | 2026-08-28 | 43
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2026-07-20 | 2026-08-28 | 40
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2026-08-03 | 2026-08-21 | 19
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2026-08-03 | 2026-08-28 | 26
DDG 103 | TRUXTUN | Norfolk | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-04 | 33
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-25 | 54
LPD 19 | MESA VERDE | Norfolk | CMAV (A) | ACTIVE | 2026-08-10 | 2026-12-18 | 131
LSD 50 | CARTER HALL | Little Creek | CMAV (A) | ACTIVE | 2026-08-24 | 2027-01-08 | 138
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2026-08-24 | 2026-10-02 | 40
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2026-08-24 | 2026-11-01 | 70
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2026-08-31 | 2026-09-27 | 28
DDG 124 | HARVEY C BARNUM JR | Norfolk | CMAV (A) | ACTIVE | 2026-09-03 | 2026-10-12 | 40
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2026-09-08 | 2026-10-02 | 25
DDG 95 | JAMES E WILLIAMS | Norfolk | CMAV (A) | ACTIVE | 2026-09-08 | 2026-10-09 | 32
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-30 | 47
DDG 103 | TRUXTUN | Norfolk | CMAV (A) | ACTIVE | 2026-09-15 | 2026-11-01 | 48
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2026-10-13 | 2027-01-08 | 88
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2026-10-19 | 2026-11-06 | 19
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2026-10-19 | 2026-11-13 | 26
LHD 5 | BATAAN | Norfolk | CMAV (A) | ACTIVE | 2026-10-26 | 2026-12-18 | 54
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-08 | 47
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-18 | 57
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2026-11-23 | 2027-02-19 | 89
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-15 | 47
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 95 | JAMES E WILLIAMS | Norfolk | CMAV (A) | ACTIVE | 2027-03-01 | 2027-04-09 | 40
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2027-03-15 | 2027-04-23 | 40
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2027-03-29 | 2027-04-23 | 26
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2027-03-29 | 2027-04-23 | 26
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2027-03-29 | 2027-04-23 | 26
LPD 19 | MESA VERDE | Norfolk | CMAV (A) | ACTIVE | 2027-04-05 | 2027-04-23 | 19
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2027-04-05 | 2027-04-23 | 19
LSD 50 | CARTER HALL | Little Creek | CMAV (A) | ACTIVE | 2027-04-12 | 2027-04-30 | 19
LSD 51 | OAK HILL | Little Creek | CMAV (A) | ACTIVE | 2027-04-19 | 2027-06-17 | 60
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2027-05-03 | 2027-05-21 | 19
DDG 67 | COLE | Norfolk | CMAV (A) | ACTIVE | 2027-05-10 | 2027-06-17 | 39
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2027-05-10 | 2027-06-17 | 39
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2027-05-24 | 2027-09-17 | 117
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## SERMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2026-01-05 | 2026-07-03 | 180
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2026-04-06 | 2026-07-03 | 89
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2026-05-18 | 2026-07-10 | 54
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2026-06-15 | 2026-07-24 | 40
LCS 31 | CLEVELAND | Mayport | CMAV (A) | ACTIVE | 2026-06-15 | 2026-09-18 | 96
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2026-07-13 | 2026-07-31 | 19
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-14 | 33
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-21 | 40
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2026-07-29 | 2026-08-20 | 23
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-08-03 | 2026-08-28 | 26
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-18 | 40
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2026-08-17 | 2026-09-25 | 40
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2026-08-24 | 2026-09-11 | 19
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2026-08-24 | 2026-10-02 | 40
LCS 29 | BELOIT | Mayport | CMAV (A) | ACTIVE | 2026-09-07 | 2027-04-16 | 222
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2026-09-14 | 2026-10-23 | 40
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2026-09-21 | 2026-10-11 | 21
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-13 | 33
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-13 | 33
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-13 | 33
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2026-10-13 | 2026-11-20 | 39
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2026-10-19 | 2026-11-27 | 40
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2026-10-19 | 2026-12-11 | 54
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2026-11-09 | 2027-01-08 | 61
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2026-11-16 | 2027-01-10 | 56
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2026-11-16 | 2027-01-15 | 61
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2026-12-18 | 19
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2027-01-04 | 2027-01-29 | 26
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2027-01-04 | 2027-02-12 | 40
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2027-01-19 | 2027-02-21 | 34
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2027-01-19 | 2027-02-26 | 39
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2027-02-01 | 2027-03-12 | 40
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2027-02-16 | 2027-03-26 | 39
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-12 | 19
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-12 | 19
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-12 | 19
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-19 | 26
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-19 | 26
DDG 122 | JOHN BASILONE | Mayport | CMAV (A) | ACTIVE | 2027-05-03 | 2027-06-14 | 43
LCS 31 | CLEVELAND | Mayport | CMAV (A) | ACTIVE | 2027-05-03 | 2027-11-30 | 212
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2027-05-10 | 2027-06-20 | 42
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2027-05-17 | 2027-06-25 | 40
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2027-05-17 | 2027-06-25 | 40
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2027-05-24 | 2027-06-18 | 26
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2027-06-01 | 2027-07-09 | 39
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2027-06-21 | 2027-07-30 | 40
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## SWRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2026-05-11 | 2026-07-24 | 75
LSD 42 | GERMANTOWN | San Diego | CMAV (A) | ACTIVE | 2026-05-26 | 2026-09-18 | 116
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2026-05-29 | 2026-07-17 | 50
LCS 26 | MOBILE | San Diego | CMAV (A) | ACTIVE | 2026-06-01 | 2026-07-12 | 42
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2026-06-15 | 2026-08-03 | 50
DDG 92 | MOMSEN | San Diego | CMAV (A) | ACTIVE | 2026-06-16 | 2026-07-24 | 39
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2026-06-22 | 2026-07-31 | 40
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2026-06-29 | 2026-08-21 | 54
CG 70 | LAKE ERIE | San Diego | CMAV (A) | ACTIVE | 2026-06-29 | 2026-09-23 | 87
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2026-07-06 | 2026-08-14 | 40
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-21 | 40
LCS 12 | OMAHA | San Diego | CMAV (A) | ACTIVE | 2026-07-13 | 2026-08-21 | 40
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-18 | 40
CG 65 | CHOSIN | San Diego | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-20 | 42
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2026-08-10 | 2026-09-21 | 43
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2026-08-29 | 2026-10-07 | 40
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2026-08-31 | 2026-09-25 | 26
LHD 8 | MAKIN ISLAND | San Diego | CMAV (A) | ACTIVE | 2026-08-31 | 2026-09-25 | 26
LPD 26 | JOHN P MURTHA | San Diego | CMAV (A) | ACTIVE | 2026-09-01 | 2026-09-23 | 23
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2026-09-01 | 2026-10-21 | 51
DDG 63 | STETHEM | San Diego | CMAV (A) | ACTIVE | 2026-09-07 | 2026-11-27 | 82
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2026-09-21 | 2026-10-30 | 40
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2026-09-21 | 2026-10-30 | 40
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-03 | 30
DDG 92 | MOMSEN | San Diego | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-13 | 40
LCS 38 | PIERRE | San Diego | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-20 | 40
CG 62 | ROBERT SMALLS | San Diego | CMAV (A) | ACTIVE | 2026-10-12 | 2026-11-20 | 40
CG 71 | CAPE ST GEORGE | San Diego | CMAV (A) | ACTIVE | 2026-10-12 | 2026-12-11 | 61
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2026-10-13 | 2026-12-13 | 62
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2026-11-02 | 2026-12-11 | 40
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2026-11-09 | 2027-01-08 | 61
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2026-11-17 | 2027-01-08 | 53
LCS 26 | MOBILE | San Diego | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-08 | 47
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2026-11-23 | 2027-02-12 | 82
LCS 12 | OMAHA | San Diego | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-11 | 43
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-27 | 59
DDG 93 | CHUNG-HOON | San Diego | CMAV (A) | ACTIVE | 2026-12-14 | 2027-01-08 | 26
DDG 97 | HALSEY | San Diego | CMAV (A) | ACTIVE | 2027-01-08 | 2027-02-18 | 42
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-19 | 40
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-22 | 43
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-26 | 47
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-02-26 | 47
DDG 1000 | ZUMWALT | San Diego | CMAV (A) | ACTIVE | 2027-01-11 | 2027-03-09 | 58
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2027-01-18 | 2027-05-08 | 111
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2027-01-25 | 2027-03-07 | 42
LCS 36 | KINGSVILLE | San Diego | CMAV (A) | ACTIVE | 2027-02-01 | 2027-03-26 | 54
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2027-02-05 | 2027-03-12 | 36
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2027-02-08 | 2027-03-19 | 40
LPD 27 | PORTLAND | San Diego | CMAV (A) | ACTIVE | 2027-02-08 | 2027-03-26 | 47
CG 71 | CAPE ST GEORGE | San Diego | CMAV (A) | ACTIVE | 2027-02-22 | 2027-03-26 | 33
DDG 125 | JACK H LUCAS | San Diego | CMAV (A) | ACTIVE | 2027-02-22 | 2027-04-02 | 40
LCS 30 | CANBERRA | San Diego | CMAV (A) | ACTIVE | 2027-03-08 | 2027-03-29 | 22
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2027-03-15 | 2027-04-23 | 40
DDG 93 | CHUNG-HOON | San Diego | CMAV (A) | ACTIVE | 2027-05-11 | 2027-06-30 | 51
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## NWRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2026-05-04 | 2026-07-03 | 61
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2026-10-26 | 2026-12-04 | 40
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2026-11-16 | 2026-12-30 | 45
DDG 52 | BARRY | Everett | CMAV (A) | ACTIVE | 2026-11-23 | 2027-01-08 | 47
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2027-02-15 | 2027-03-13 | 27
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## HRMC
Hull | Ship | Homeport | Type | Status | Start Date | End Date | Duration (D)
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2026-05-26 | 2026-07-03 | 39
CG 67 | SHILOH | Pearl Harbor | CMAV (A) | ACTIVE | 2026-06-22 | 2026-09-23 | 94
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2026-08-03 | 2026-09-11 | 40
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2026-08-07 | 2026-09-08 | 33
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2026-09-14 | 2026-11-06 | 54
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2026-09-29 | 2026-11-08 | 41
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2026-10-05 | 2026-11-06 | 33
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-08 | 40
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2026-11-30 | 2027-01-22 | 54
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2027-01-19 | 2027-02-05 | 18
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2027-02-25 | 2027-03-26 | 30
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2027-03-01 | 2027-04-09 | 40
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2027-03-15 | 2027-04-23 | 40
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2027-04-19 | 2027-06-03 | 46
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2027-05-10 | 2027-06-11 | 33
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2027-06-14 | 2027-07-23 | 40
“This information is to provide U.S. DoW industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoW industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”